## Sheet1
|  |  | Contract Number | Sponsor | Project Name | Contract Start Date | Contract End Date | 2011-01-05 |  | Authorized Funds | Disbursed Funds | Available Balance | Present % Contract Duration | % Funds Disbursed | Variance | Status
Contract ended: funds to be recouped | x |  | C40-4060 | Sharing Community | S+C | 2004-12-01 | 2005-11-30 | 2011-01-05 |  | 363828 | 208529 | 155299 | 100% | 57.32% | -42.68% | CLOSED- HUD contacted to recoup
| x |  | C50-4058 | Sharing Community | S+C | 2006-02-01 | 2007-01-31 | 2011-01-05 |  | 380304 | 371547 | 8757 | 100% | 97.7% | -2.303% | CLOSED- HUD contacted to recoup
|  | x | B50-4005 | Sharing Community | HOST II | 2006-02-01 | 2007-01-31 | 2011-01-05 |  | 236659 | 225390 | 11269 | 100% | 95.24% | -4.762% | CLOSED- HUD contacted to recoup
|  | x | B50-4010 | Westhab | OWN 1 | 2006-08-01 | 2007-07-31 | 2011-01-05 |  | 46941 | 44215 | 2726 | 100% | 94.19% | -5.807% | CLOSED- HUD contacted to recoup
Pre-esnaps contracts open |  | bad | B40-4003 | YMCA | Supportive Housing SRO | 2007-12-01 | 2010-11-30 | 2011-01-05 | 1.0329 | 314239 | 144758 | 169481 | 100% | 46.07% | -53.93% | 19 months behind schedule. Grant ended. Money must be drawn by 2/28/11 or funds wil be lost to HUD! | !!
| good |  | C50-4029 | YMCA | SRO S+C | 2006-09-18 | 2011-09-17 | 2011-01-05 | 0.86027 | 85440 | 79045 | 6395 | 86.03% | 92.52% | 6.488% | 4 months ahead of schedule - this project will run out of money 8 months before renewal | !!
| bad |  | C50-4034 | Westhab | SRO S+C | 2006-09-18 | 2011-09-17 | 2011-01-05 | 0.86027 | 85440 | 32040 | 53400 | 86.03% | 37.5% | -48.53% | 29 months behind schedule (with 9 left). No draws for several months – may lose funding! | !
|  | bad | B60-4025 | FSSY | Homestead II | 2008-09-23 | 2011-09-22 | 2011-01-05 | 0.76164 | 315000 | 193836 | 121164 | 76.16% | 61.54% | -14.63% | 5 months behind schedule.
| bad |  | C70-4027 | YMCA | S+C for Vets | 2009-09-24 | 2014-09-23 | 2011-01-05 | 0.25644 | 246300 | 4127 | 242173 | 25.64% | 1.676% | -23.97% | 14 months behind schedule. [Should add additional clients]
| bad |  | C70-4029 | St. John's Riverside | S+C | 2008-10-01 | 2013-09-30 | 2011-01-05 | 0.4526 | 98520 | 19462 | 79058 | 45.26% | 19.75% | -25.51% | 15 months behind schedule (with 33 left) [Should add third client]. No draws for several months – may lose funding! | !
FY08 |  |  | 478-B2T040801 | FSSY | Homestead | 2009-06-01 | 2010-05-31 | 2011-01-05 | 1.5973 | 180713 | 180421 | 292 | 100% | 99.84% | -0.1616% | On schedule. HUD will recoup $292
|  |  | 484-B2T040801 | Mt. Vernon NHC | Medical & Substance Abuse Outreach | 2009-10-01 | 2010-09-30 | 2011-01-05 | 1.263 | 73049 | 73049 | 0 | 100% | 100% | 0% | On schedule – voucher on hold pending HUD review of timesheets
All other FY08 are fully drawn down
FY09 |  | good | 476-B2T040802 | Greyston | Family Inn | 2010-02-01 | 2011-01-31 | 2011-01-05 | 0.92603 | 66474 | 51717 | 14757 | 92.6% | 77.8% | -14.8% | On schedule
|  | good | 478-B2T040802 | FSSY | Homestead | 2010-06-01 | 2011-05-31 | 2011-01-05 | 0.59726 | 180713 | 85717 | 94996 | 59.73% | 47.43% | -12.29% | On schedule.
|  | good | 479-B2T040802 | Sharing Community | HOST II | 2010-02-01 | 2011-01-31 | 2011-01-05 | 0.92603 | 236659 | 214080 | 22579 | 92.6% | 90.46% | -2.143% | On schedule
|  | good | 482-B2T040802 | YWCA | JobPlus | 2010-02-01 | 2011-01-31 | 2011-01-05 | 0.92603 | 46034 | 39374 | 6660 | 92.6% | 85.53% | -7.07% | On schedule.
|  | bad | 484-B2T040802 | Mt. Vernon NHC | Medical & Substance Abuse Outreach | 2010-10-01 | 2011-09-30 | 2011-01-05 | 0.26301 | 73049 | 4645 | 68404 | 26.3% | 6.359% | -19.94% | 2 months behind schedule – voucher on hold pending HUD review of timesheets
| bad |  | 496-C2T040802 | Sharing Community | S+C | 2010-02-01 | 2011-01-31 | 2011-01-05 | 0.92603 | 468384 | 116656 | 351728 | 92.6% | 24.91% | -67.7% | 8 months behind schedule. Vouchers submitted, but dealyed due to HUD review of leases
|  | bad | 497-B2T040802 | My Sister’s Place | Shelter Legal Services | 2010-02-01 | 2011-01-31 | 2011-01-05 | 0.92603 | 15364 | 11122 | 4242 | 92.6% | 72.39% | -20.21% | 2 months behind schedule.
|  | bad | 503-B2T040802 | Westhab | Yonkers OWN 1 | 2010-08-01 | 2011-07-31 | 2011-01-05 | 0.43014 | 48729 | 11625 | 37104 | 43.01% | 23.86% | -19.16% | 2 months behind schedule.
|  | good | 504-B2T040802 | Westhab | Yonkers OWN 4 | 2010-02-01 | 2011-01-31 | 2011-01-05 | 0.92603 | 32333 | 29285 | 3048 | 92.6% | 90.57% | -2.03% | On schedule
|  | good | 505-B2T040802 | Westhab | Yonkers OWN 2-3 | 2010-02-01 | 2011-01-31 | 2011-01-05 | 0.92603 | 102274 | 86040 | 16234 | 92.6% | 84.13% | -8.476% | On schedule.