## Status
Yonkers Truancy Reduction Strategy Group
2008-09 Policy Implementation Status Report (as of 1/30/09)
Date | # Students with 20+* absences | # Ed Neglect Reports Received by YPS Central Office | # Supplemental Forms Received by YPS Central Office | Other Ed Neglect reports received (less than 20 days | # Ed Neglect Cases Accepted by CSR- PRIOR YEAR | # Ed Neglect Cases Accepted by CSR-CURRENT YEAR | Year-To-Year % Change in Volume of Ed Neglect Cases Accepted by CSR | # Ed Neglect Investigations Pending | # Ed Neglect Investigations Completed | # Ed Neglect Cases Indicated | % Ed Neglect Cases Indicated***
9/4/08–10/08/08 | 16 | 0 | 0 | 3 | 34 | 27 | -20.59% | 26 | 1 | 0 | 0%
9/4/08-11/10/08 [-11/12/08 for CPS stats] | 34 | 9 | 10 | 14 | 61 | 61 | 0% | 57 | 4 | 1 | 25%
9/4/08-12/01/08 | 31 | 15 | 16 | 28 | 117 | 94 | -19.66% | 33 | 0 | 0 | N/A
9/4/08-1/31/09 | 116 | 55 | 58 | 45 | 284 | 170 | -40.14% | 84 | 86 | 20 | 23.26%
* unexcused or unexplained
grades 1 to 8

## Rate
Changes in Rate of Educational Neglect Reporting
With Comparison to Prior Year
|  | CURRENT YEAR |  | PRIOR YEAR
Date | # Total Days (NOT Just School Days) Since Last Summary | # Ed Neglect Cases Accepted by CSR Since Last Summary | REPORTING RATE: Average # of Reports Filed Per Day Since Last Summary | # Ed Neglect Cases Accepted by CSR Since Last Summary | REPORTING RATE: Average # of Reports Filed Per Day Since Last Summary
9/1/07–11/15/07 | 76 | 63 | 0.82895 | 63 | 0.82895
9/1/07–12/5/2007 | 20 | 4 | 0.2 | 43 | 0.93478
9/1/07–12/31/2007 | 26 | 68 | 2.6154
9/1/07-2/20/2008 | 51 | 207 | 4.0588 | 75 | 1.4706
9/01/07–3/20/08 | 29 | 47 | 1.6207 | 43 | 1.4828
9/01/07–4/11/08 | 22 | 83 | 3.7727 | 24 | 1.0909
9/01/07–5/22/08 | 41 | 79 | 1.9268 | 53 | 1.2927