## Sheet1
| Contract Number | Sponsor | Project Name | Contract Start Date | Contract End Date | 2010-10-01 |  | Authorized Funds | Disbursed Funds | Available Balance | Present % Contract Duration | % Funds Disbursed | Variance | Status
Contract ended: funds to be recouped | B10-4009 | Sharing Community | JumpStart | 2005-05-01 | 2007-04-30 | 2010-10-01 |  | 370539 | 348036 | 22503 | 100% | 93.93% | -6.073% | CLOSED- HUD contacted to recoup
| B50-4005 | Sharing Community | HOST II | 2006-02-01 | 2007-01-31 | 2010-10-01 |  | 236659 | 225390 | 11269 | 100% | 95.24% | -4.762% | CLOSED- HUD contacted to recoup
| C40-4060 | Sharing Community | S+C | 2004-12-01 | 2005-11-30 | 2010-10-01 |  | 363828 | 208529 | 155299 | 100% | 57.32% | -42.68% | CLOSED- HUD contacted to recoup
| C50-4058 | Sharing Community | S+C | 2006-02-01 | 2007-01-31 | 2010-10-01 |  | 380304 | 371547 | 8757 | 100% | 97.7% | -2.303% | CLOSED- HUD contacted to recoup
| B00-4023 | Victims Asst. Services | Yonkers Anti-violence Project | 2001-04-01 | 2003-03-31 | 2010-10-01 |  | 82000 | 69228 | 12772 | 100% | 84.42% | -15.58% | No longer in LOCCS. Recouped?
| B50-4010 | Westhab | OWN 1 | 2006-08-01 | 2007-07-31 | 2010-10-01 |  | 46941 | 44215 | 2726 | 100% | 94.19% | -5.807% | CLOSED- HUD contacted to recoup
Pre-esnaps contracts open | B40-4003 | YMCA | Supportive Housing SRO | 2007-12-01 | 2010-11-30 | 2010-10-01 | 0.94521 | 314239 | 136874 | 177365 | 94.52% | 43.56% | -50.96% | 18 months behind schedule. Grant ends in 2 months- draw down ASAP | !
| C50-4029 | YMCA | SRO S+C | 2006-09-18 | 2011-09-17 | 2010-10-01 | 0.80767 | 85440 | 55706 | 29734 | 80.77% | 65.2% | -15.57% | 9 months behind schedule (with 11 left) [Should add additional clients] | !
| C50-4034 | Westhab | SRO S+C | 2006-09-18 | 2011-09-17 | 2010-10-01 | 0.80767 | 85440 | 32040 | 53400 | 80.77% | 37.5% | -43.27% | 26 months behind schedule (with 11 left). [Should add additional clients]. No draws since last meeting | !
| B60-4025 | FSSY | Homestead II | 2008-09-23 | 2011-09-22 | 2010-10-01 | 0.67397 | 315000 | 173489 | 141511 | 67.4% | 55.08% | -12.32% | 4 months behind schedule. No draws since last meeting. | !
| C70-4027 | YMCA | S+C for Vets | 2009-09-24 | 2014-09-23 | 2010-10-01 | 0.20384 | 246300 | 1585 | 244715 | 20.38% | 0.6435% | -19.74% | 12 months behind schedule. No draws since last meeting. [Should add additional clients] | !
| C70-4029 | St. John's Riverside | S+C | 2008-10-01 | 2013-09-30 | 2010-10-01 | 0.4 | 98520 | 14607 | 83913 | 40% | 14.83% | -25.17% | 15 months behind schedule (with 36 left) [Should add third client]. No draws since last meeting | !
FY08 | 478B-B2T040801 | FSSY | Homestead | 2009-06-01 | 2010-05-31 | 2010-10-01 | 1.3342 | 180713 | 180421 | 292 | 100% | 99.84% | -0.1616% | On schedule. HUD will recoup $292
| 484B-B2T040801 | Mt. Vernon NHC | Medical & Substance Abuse Outreach | 2009-10-01 | 2010-09-30 | 2010-10-01 | 1 | 73049 | 50522 | 22527 | 100% | 69.16% | -30.84% | 3 months behind schedule. Voucher July through September ASAP. Grant ended 9/30/10; grant closes 12/29/10. | !
All other FY08 are fully drawn down
FY09 | 476-B2T040802 | Greyston | Family Inn | 2010-02-01 | 2011-01-31 | 2010-10-01 | 0.66301 | 66474 | 43279 | 23195 | 66.3% | 65.11% | -1.195% | On schedule
| 478-B2T040802 | FSSY | Homestead | 2010-06-01 | 2011-05-31 | 2010-10-01 | 0.33425 | 180713 | 0 | 180713 | 33.42% | 0% | -33.42% | Contract now executed, 4 months into 12 month period. Voucher submitted 9/13 for first 3 months. Should voucher for September.
| 479-B2T040802 | Sharing Community | HOST II | 2010-02-01 | 2011-01-31 | 2010-10-01 | 0.66301 | 236659 | 133236 | 103423 | 66.3% | 56.3% | -10% | On schedule. Voucher for September.
| 482-B2T040802 | YWCA | JobPlus | 2010-02-01 | 2011-01-31 | 2010-10-01 | 0.66301 | 46034 | 21792 | 24242 | 66.3% | 47.34% | -18.96% | 2 months behind schedule. Voucher for August and September ASAP. | !
| 484-B2T040802 | Mt. Vernon NHC | Medical & Substance Abuse Outreach | 2010-10-01 | 2011-09-30 | 2010-10-01 | 0 | 73049 | NA | #VALUE! | 0% | #VALUE! | 0% | Contract has not yet been executed due to poor financial management.
| 496-C2T040802 | Sharing Community | S+C | 2010-02-01 | 2011-01-31 | 2010-10-01 | 0.66301 | 468384 | 0 | 468384 | 66.3% | 0% | -66.3% | First voucher in process. Should submit second voucher.
| 497-B2T040802 | My Sister’s Place | Shelter Legal Services | 2010-02-01 | 2011-01-31 | 2010-10-01 | 0.66301 | 15364 | 6304 | 9060 | 66.3% | 41.03% | -25.27% | 3 months behind schedule. Voucher for July, August and September ASAP. | !
| 503-B2T040802 | Westhab | Yonkers OWN 1 | 2010-08-01 | 2011-07-31 | 2010-10-01 | 0.16712 | 48729 | 3875 | 44854 | 16.71% | 7.952% | -8.76% | On schedule. Voucher for September.
| 504-B2T040802 | Westhab | Yonkers OWN 4 | 2010-02-01 | 2011-01-31 | 2010-10-01 | 0.66301 | 32333 | 21765 | 10568 | 66.3% | 67.32% | 1.014% | On schedule
| 505-B2T040802 | Westhab | Yonkers OWN 2-3 | 2010-02-01 | 2011-01-31 | 2010-10-01 | 0.66301 | 102274 | 56819 | 45455 | 66.3% | 55.56% | -10.75% | On schedule. Voucher for September.