# Yonkers Juvenile Crime Enforcement Coalition

## Meeting Minutes

## May 19, 2009

Meeting Facilitator(s): Karl Bertrand and Roberta West

### Present:

| K. Bertrand, PD&D | C. Lurry, Andrus | P. Selzer, DSS |
| --- | --- | --- |
| K. Blumenthal, Student Advocacy | A. Mantsios, USAO | Y. Spiegel, PD&D |
| R. Childs, Big Brothers/ Big Sisters, FSW | A. Margolis, Andrus | J. Thompson, YMCA |
| T. Gaynor, School Mediation Coordinator | K. Mines, Westhab Weed & Seed | L. Vargas, Andrus |
| M. Gerkins, Big Brothers/ Big Sisters, FSW | T. Mitchell, Big Brothers/ Big Sisters, FSW | P.O. R. West, Planning Unit YPD |
| L. Heyward, YCAP | A. Newman, WJCS | P. White, DCMH |
| S. P. Howard, YMCA | R. Nightingale, Westhab | G. Winn, DSS |
| M. Khaleel, KFL Inc. | J. Parsinnen, Westhab | S. Zaluski, YPS |

TOPICS:

# Welcomes and Introduction

- Announcements:

  - Yonkers Drug Free Coalition will be hosting a site visit from district manager in July. It is desirable to show activity in Yonkers before the site visit. We will distribute Social Host Law information from the District Attorney to parents, since our data shows most kids get alcohol in their home or a friend’s home.

  - Youth Board Award Program recognizes 11th graders who are exemplary volunteers/ citizens. If you know a worthy student who qualifies, then nominate her or him at the Youth Board website by the end of June deadline. what data to gather.

- Review of minutes from 4/21/09-Email any necessary changes.

- Year 1 DCJS implementation grades

Andrus SFP training		Trained 5 agencies		A grade

BBBS				Matched 20 mentors		A

FFT				Project canceled		Inc.

SFP				YCAP				A

Westhab			A

YMCA			F

CLUSTER			Inc.

Family Ties			A

Suspension intervention	Only screened 9 students	D

Overall management	Poor financial management	C+

& program implementation

We need better quarterly reporting and vouchering. PD&D should design better forms to facilitate this goal.

- Year 1 4th quarter DCJS performance measures.

See handout.

BBBS met targets for mentor recruitment and matches. No outcome data yet.

SFP met agency training, number of youth target, and outcome measure targets.

Suspension intervention did not meet targets (only linked 5 youth to services).

- Year 2 SFP for children aged 6-11

Longer, more intensive 14 session semesters; model adapted to younger children. Andrus will train 5 agencies in this new model. Sign up in the next month. Possible agencies include: Westhab, YMCA, Family Ties, FSW, YCAP, Probation, Lexington Center, HOPE

It is difficult to get good attendance at SFP sessions even with 7 session semesters. Saturday sessions are no better. How to improve attendance with 14 sessions?

We can use former participants’ testimonials to encourage new parents to attend and complete the program. We might even use former participants as co-leaders for new semesters.

Can CPS mandate attendance? No, CPS can encourage attendance only. Chris Haywood should contact CPS staff to familiarize them with SFP program in Yonkers. Family Court judges can mandate participation.

Run sessions at schools, churches, probation offices.

Parents of younger children are still more involved in parenting them. It is likely that more sessions will be attended for this new model.

- Implementation of Year 2 DCJS grant

a. BBBS: 20 continuing matches from Year 1. 20 new matches to be formed in Year 2. Need more male mentors! We have female mentors waiting, but we want at least 10 male mentors to be matched with boys on the wait-list.

b. SFP: Agencies should determine when Year 2 funded sessions will be held. Contact Y. Spiegel with that information. SFP 6-11 training will be organized by end of June.

c. Suspension Intervention Assessment program:

Andrus must create an implementation plan. If students are not engaged and linked within 60 days, try another plan.

Andrus can Child Study Teams inside schools to get info on needy students. These groups are already formed to deal with kids with learning and behavior problems.

Next meeting: June 16, 2009