| Grant Number | Sponsor | Program | Vouchering activity and grant status |
| --- | --- | --- | --- |
| FY05-FY07 Contracts |  |  |
| C50-4029 | YMCA | SRO S+C | Hold placed on grant due to missing APR. |
| C50-4034 | Westhab | SRO S+C | 18 months behind schedule. May need to lease extra units. |
| C70-4029 | St. John's Riverside | S+C | 10 months behind schedule. |
| B40-4003 | YMCA | Supportive Housing SRO | Lisa Lockley promised to lift hold and process voucher on 10/27/09 |
| B60-4025 | FSSY | Homestead II | 3 months behind schedule |
| B70-4012 | Mt. Vernon NHC | Medical & Substance Abuse Outreach | Closes 10/30- Fully drawn down |
| B70-4016 | Westhab | Yonkers OWN 1 | Closes 10/30- Fully drawn down |
| B70-4022 | FSSY | Homestead | Grant ended 5/31/09 Remaining balance of $36,974 will be recouped. Voucher request is under review by HUD. |
| FY08 Contracts |  |  |
| 0472-B2T040802 | Andrus | Family Care | Ahead of schedule |
| 0476-B2T040802 | Greyston | Family Inn | Has not yet vouchered. 9 months behind schedule. |
| 0478-B2T040802 | FSSY | Homestead | On schedule |
| 0479-B2T040802 | Sharing Community | HOST II | 3 months behind schedule. |
| 0482-B2T040802 | YWCA | JobPlus | $24,316 voucher is under review |
| 0484-B2T040802 | MVNHC | Medical and Substance Abuse Outreach | Contract not yet executed. |
| 0496-C2T040802 | Sharing Community | S+C | On schedule |
| 0497-B2T040802 | My Sister’s Place | Shelter Legal Services | On schedule |
| 0503-B2T040802 | Westhab | Yonkers OWN 1 | On schedule |
| 0504-B2T040802 | Westhab | Yonkers OWN 4 | 4 months behind schedule |
| 0505-B2T040802 | Westhab | Yonkers OWN 2-3 | 4 months behind schedule |