Fund Drawdown Report for Yonkers CoC as of September 2009


	Grant Number
	Sponsor
	Program
	Vouchering activity and grant status 

	C50-4029
	YMCA
	SRO S+C
	Hold to be lifted on grant- should voucher soon.

	C50-4034
	Westhab
	SRO S+C
	Additional vouchers should be submitted: 31% (19 months) behind schedule.

	C70-4029
	St. John's Riverside
	S+C
	10 months behind schedule (just leased second apartment)

	B40-4003
	YMCA
	Supportive Housing SRO
	Hold just lifted on grant- should voucher very soon.

	B60-4025
	FSSY
	Homestead II
	

	B70-4012
	Mt. Vernon NHC
	Medical & Substance Abuse Outreach
	31% (4 months) behind schedule. Grant ends 9/30- should voucher ASAP

	B70-4016
	Westhab
	Yonkers OWN 1
	

	B70-4022
	FSSY
	Homestead
	Grant ended 5/31/09

FUNDS LOST TO HUD! Remaining balance of $36,974 will be recouped.

	
	
	
	

	NEW FY08 Contracts
	
	

	0472-B2T040802
	Andrus 
	Family Care
	

	0476-B2T040802
	Greyston
	Family Inn
	Has not yet vouchered. 8 months behind schedule.

	0478-B2T040802
	FSSY
	Homestead
	Has not yet vouchered. 4 months behind schedule.

	0479-B2T040802
	Sharing Community
	HOST II
	Has not yet vouchered. 8 months behind schedule.

	0482-B2T040802
	YWCA
	JobPlus
	

	0496-C2T040802
	Sharing Community
	S+C
	

	0497-B2T040802
	My Sister’s Place
	Shelter Legal Services
	Has not yet vouchered. 8 months behind schedule.

	0503-B2T040802
	Westhab
	Yonkers OWN 1
	

	0504-B2T040802
	Westhab
	Yonkers OWN 4
	

	0505-B2T040802
	Westhab
	Yonkers OWN 2-3
	


