Revised Schedule of Key Dates for FY08 Continuum of Care Application

(Revised 5/30/08)

| Date | Milestone |
| --- | --- |
| 2/21/08 | Westchester received debriefing from HUD on our prior application score |
| 3/20/08 | General section of FY08 SuperNOFA published in Federal Register |
| 4/16/08 | Blank pre-applications and instructions to be distributed for renewal projects |
| 5/5/08 | Blank pre-applications and instructions to be distributed for new projects |
| May 08 | HUD provides training for applicants in how to use new on-line application system |
| May 08 | Partnership conducts outreach to potential new CoC participants and disseminates information about high-priority needs and tiering system for this year’s application. |
| 5/19/08 4:00 p.m. | Deadline for renewal projects to submit pre-applications, including documentation that they meet the performance standard* and HMIS eligibility standard** in order to participate in this year’s application. |
| 6/16/08 4:00 p.m. | Deadline for new projects to submit two-page pre-applications |
| 7/1/08 9:00 – 12:00 | Confirmed date for public vote to determine FY08 project priorities APPROXIMATE SCHEDULE: 9:00–9:30: Voter sign-in and distribution of numbered ballots 9:30–10:15: Brief presentations on potential new projects 10:15–10:45: Voting 10:45–11:45: Vote tallying Yonkers Public Library, Grinton I. Will Branch – auditorium 1500 Central Park Avenue, Yonkers free parking available, for directions go to www.ypl.org |
| 7/1/08 | HUD expected to issue CoC application (earliest possible date) |
| July 08 | Sponsors prepare application Exhibits |
| 7/22/2008 | Tentative date sponsors must submit completed applications to applicant agencies |
| 7/31/08 | Anticipated date of submission of complete consolidated application to HUD |
| unknown | Deadline for submission of complete consolidated application to HUD |

* Performance eligibility standard for renewal applications: Existing CoC-funded projects will only be eligible for renewal if the project’s most recently submitted APR shows that it has met 100% of at least 2 of its 3 outcome goals and at least 80% of the remaining goal.

** HMIS eligibility standard for renewal applications: Existing CoC-funded projects will only be eligible for renewal if the if the sponsoring agency has entered at least 90% of all clients served in the project between 1/1/08 and 3/31/08 into Westchester's Homeless Management Information System (HMIS), including completion of the entire workflow process.