Fund Drawdown Report for Yonkers CoC as of 1/21/2009


	Grant Number
	Sponsor
	Program
	Vouchering activity and grant status 

	C50-4029
	YMCA
	SRO S+C
	Hold placed on grant

	C50-4034
	Westhab
	SRO S+C
	$12,816 released 12/30/08. Additional vouchers should be submitted- 30% behind schedule

	C70-4027
	YMCA
	S+C for Vets
	Grant not yet executed

	C70-4029
	St. John's Riverside
	S+C
	No vouchers yet submitted

	C70-4032
	Sharing Community
	S+C
	Vouchers processed 12/30/09. Drawdowns on schedule.

	B40-4003
	YMCA
	Supportive Housing SRO
	Hold placed on grant

	B60-4025
	FSSY
	Homestead II
	Vouchers for only $4,183 submitted; Grant is now 15% behind schedule

	B70-4009
	Sharing Community
	HOST II
	28% behind schedule. Please submit Vouchers for remainder of authorized funds at end of 4Q on 1/31/09 

	B70-4011
	My Sister's Place
	Shelter Legal Services
	Hold placed on grant

	B70-4012
	Mt. Vernon NHC
	Medical & Substance Abuse Outreach
	Vouchers submitted 1/6/09. Drawdowns ahead of schedule.

	B70-4014
	Greyston
	Lifeskills
	Vouchers submitted. Drawdowns on schedule.

	B70-4015
	YWCA
	Job Plus
	Vouchers submitted, Funds promised 1/12/09; vouchers still “awaiting review”

	B70-4016
	Westhab
	Yonkers OWN 1
	Previous vouchers processed; more should be submitted 14% behind schedule

	B70-4018
	Andrus
	Family Care
	Vouchers submitted. Drawdowns on schedule.

	B70-4022
	FSSY
	Homestead
	Vouchers submitted to end September only. Additional vouchers should be submitted- 23% behind schedule

	B70-4021
	Westhab
	Yonkers OWN 2-3
	Waiting for budget mod approval

	B70-4024
	Westhab
	Yonkers OWN 4
	Waiting for budget mod approval


