# Yonkers Continuum of Care for the Homeless

## Meeting Minutes

## April 19, 2010

Meeting Facilitator: Yoav Spiegel

### Present:

| S. Elraheb, My Sister's Place | S. Moraldo, MVNHC | E. Waldman, Greyston |
| --- | --- | --- |
| C. Kane, FSSY | K. McGill, YMCA of Yonkers | R. Wasserman, Greyston |
| A. Koffi, YWCA | Y. Spiegel, PD&D | R. Zopf, Sharing Community |

TOPICS:

# Welcomes and Introduction

# Announcements

Westchester Eviction Prevention Network is hosting a Housing Resource Workshop on April 23 at the YWCA of White Plains.

Westhab is managing Greyston's Issan House for HIV/AIDS. There are currently many vacancies at this facility in SRO units with kitchenette/bathroom, medical case manager, 24 hr security, intensive support for high needs population. Call Ken Wray at 345-2800 x17 to refer.

- FY10 CoC Application

a. Forum held on April 14 to discuss County priorities for new projects. Speakers spoke to the need for street outreach, home finding, housing for youth (esp. those aging out of foster care), and permanent housing in Yonkers. Proposals for projects addressing those needs are likely to be requested by the County CoC Partnership.

b. Timeline for application process:

The County will register by agreeing to Pro-Rata Need (PRN) level and submitting Grant Inventory Worksheets (GIWs) in May. GIWs will list all grants being renewed in 2010. Any grant left off the GIW can not be renewed. The difference between the sum of all renewal projects listed on the GIW and the PRN is the amount of money available for new projects.

Also in May we will submit the 2010 Housing Inventory Chart listing all homeless housing and the Point In Time count numbers (PIT count was done in January). This year, the HIC and PIT count numbers are submitted through a new website: Homeless Data Exchange (HDX) and not as part of the application Exhibit 1.

In May or June RFA for new projects will be distributed. All agencies welcome to apply. Partnership will review proposals and submit best 5-6 for vote in July.

HUD will publish application NOFA and allow editing in eSNAPS no earlier than July 1.

- APR update

3 late APRs:

Two at the YMCA: YMCA Supportive SRO and YMCA SRO S+C. Grants are suspended. Must be done ASAP. Late APRs are potential reason for defunding projects in FY10 application.

St. Johns Riverside S+C APR is also late. It appears MHA has lost the APR, so please resend signed copies and then follow up with Patty Duffy.

8 APRs are due to HUD by April 30. MSP Shelter Legal Services APR is LATE:

| Sharing Community S+C – Submitted | YWCA JobPlus-Submitted |
| --- | --- |
| Sharing Community HOST II- Submitted | Andrus Family Care-Submitted |
| My Sister's Place Shelter Legal Services- LATE for review | Westhab OWN 2-3- Approved |
| Greyston PH- Submitted | Westhab OWN 4- Approved |

- Fund draw down update

All FY08 contracts ended 1/31/10 are fully drawn down or on schedule. Westhab should voucher for final funds remaining in OWN 2-3 and OWN 4 grants.

Open FY08 contracts: FSSY Homestead is 3 months behind schedule, MVHNC is now 6 months into a grant and has $0 drawn, Westhab Yonkers OWN 1 is 3 months behind schedule.

Every open contracts from previous FY has some issue:

YMCA S+C  for Vets is now 6 months into a grant and has $0 drawn.

FSSY Homestead II is 4 months behind schedule.

YMCA SRO S+C and YMCA Supportive SRO are behind schedule but on hold due to late APRs.

St. Johns Riverside S+C is on hold pending submission of late APR.

Westhab SRO S+C should add units to increase drawn down rate. 21 months behind schedule with 19 months left.

- Next meeting date

May 24 at 11 am