# Yonkers Continuum of Care for the Homeless

# Meeting Minutes

## January 13, 2011

Meeting Facilitator: Yoav Spiegel

### Present:

| J. Cumberbatch, Westhab | R. Pennington, Westhab |
| --- | --- |
| Candice Kane, FSSY | Y. Spiegel, PD&D |
| A. Koffi, YWCA | Carmen Vasquez-Brown, St. Johns Hospital |
| K. McGill, YMCA | R. Zopf, Sharing Community |
| S. Moraldo, MVHNC |  |

TOPICS:

# Welcomes and Introduction

# Announcements

- Westchester Point-In-Time Count scheduled for night of January 26th

Street homeless in Yonkers will be counted by Yonkers PD patrol, but if any agency learns in the following few days of an individual who spent the designated night on the street, forward that information to Yoav.

DSS Shelter clients will be counted through DSS database.

Emergency shelters should use 4 question demographic survey, and forward results to Yoav.

HUD Permanent housing is not included in the PIT count.

- Fund draw down update

See handout.

FY09 contracts are all on schedule except:

Sharing Community S+C is 8 months behind schedule; HUD has placed vouchers on hold pending review. Yoav is working with HUD to resolve.

My Sisters' Place is 2 months behind schedule.

MVNHC Medical Outreach is 2 months behind schedule. So is Yonkers OWN 1.

FY08 contracts are all fully drawn down, except:

MVNHC Outreach which ended last week, has vouchers under review.

Earlier contracts:

FSSY Homestead 2 five months behind schedule

Three S+C contracts in the original 5-year grant period are significantly behind schedule (Westhab S+C SRO, YMCA S+C Vets, St. Johns Riverside HOPE S+C) – these projects must increase occupancy above target level in order to catch up and use as much of the authorized funds as possible.

YMCA S+C SRO is 4 months ahead of schedule, and will therefore run out of money before the renewal starts later this year.

V. APR update

See handout.

All Yonkers CoC APRs due so far have been submitted, including the first 7 to go in through e-snaps.

YMCA SHP SRO project last APR is due for review to Yoav in two weeks.

Then 8 APRs for projects that end on 1/31/11 will be due for review in mid-March.

- New commitment for family projects in FY10 Application

The following text was included in the Exhibit 2 application documents for FY10, committing Yonkers MHA and sponsor agencies to fulfill this requirement for projects serving families:

For projects serving families, does the applicant/sponsor have a designated staff person responsible for ensuring that children are enrolled in school and connected to the appropriate services within the community, including early childhood education programs such as Head Start, Part C of the Disabilities Education Act, and McKinney-Vento education services? YES

Given the above, agencies serving families with HUD funds should make plans to fulfill the above requirements.

Next meeting: February 10, 2011