## Sheet1
| 2013-12-21 | 2013-12-28 | 2014-01-04 | 2014-01-11 | 2014-01-18 | 2014-01-25 | 2014-02-01 | 2014-02-08 | 2014-02-15 | 2014-02-22 | 2014-03-01 | 2014-03-08 | 2014-03-15 | 2014-03-22 | 2014-03-29 | 2014-04-05
ID 45 chronic and all non-chronic homeless vets in the county
Release of intformation from VA | 2013-12-21: 2014-12-09
All county Shelters using VI/SPDAT | 2014-01-11: 2014-01-06
Outreach to all soup kitchens, pantries etc. | 2014-01-25: 2014-01-20
Outreach workers to use VI/SPAT during PIT | 2014-01-25: 2014-01-20
All Drop in Shelters Using HMIS | 2014-02-08: 2014-02-03
Outreach to religious groups | 2014-02-08: 2014-02-03
All emergency food programs are to deploy VI/SPDAT | 2014-02-22: 2014-02-17
All Shelters Using HMIS | 2014-03-01: 2014-03-03
Montrose VA Using HMIS | 2014-04-05: 2014-03-31
Everyone at VA Domiciliary has a completed VI/SPDAT | 2014-04-05: 2014-03-31
Increase non-voucher housing stock by 25 units
Contact landlords in northern county regarding reduced rates | 2013-12-21: 2014-12-23
Plan for mayoral participation in Yonkers, Mt Vernon & Peekskill | 2013-12-21: 2014-12-23
DHCR/NY LIHTC Linkings | 2014-01-11: 2014-01-06
Review Yonkers tax records | 2014-01-11: 2014-01-06
CE Astorino appeal to owners for low market rates, includes employer appeal | 2014-01-25: 2014-01-20
Go PHA opening lists for veterans | 2014-01-25: 2014-01-20
Letters go out to homeowners receiving veteran tax credit | 2014-02-08: 2014-02-03
Enlist "Patriot Employers" for 45 jobs at $15+ per hour
Get all employment resource stakeholders to the table | 2013-12-21: 2014-12-23
County WIB & Yonkers WIB join Patriot Employer effort | 2014-01-04: 2014-01-06
Add Patriot Employer page to wiki | 2014-01-04: 2014-01-06
Develop an action plan with 5 stakeholders | 2014-01-04: 2014-01-06
Find services for 45 new chronically homeless vets
DSS agreement for chronic homeless services | 2013-12-21: 2014-12-23
Peer/volunteer/FSW plan in place | 2014-01-25: 2014-01-20